## Logframe English version
Annex to the project document
Component 1 | Goal | Indicator (outputs) | Activity
1. Improved food safety and nutrition at community level | 1. Enhancing the food security and nutritional status of vulnerable families in the pilot regions of KR. | 1.1. Sustainable food production and processing are achieved by a minimum of 75% (including 30% female members) of 150 farmer groups | 1.1.1. to select 150 target farmer groups (15 people per a farmer group; in total 2,250 families in need) 1.1.2. To build capacity of 150 farmer groups on (a) diversifying their food production and (b) organic farming (by 3 workshops for each topic) 1.1.3. To provide 2 follow-up consultations for 150 farmer groups 1.1.4. To provide agricultural support (seeds, plants, livestock, etc.) to 150 farmer groups based on their needs
|  | 1.2. Improved income of the project beneficiaries (families) up to 20 % due to the new agro-technologies integration | 1.2.1. Testing and promoting new vegetable, fruit and berry varieties at community levels 1.2.1.1. To create roster of local/national fruit growing and gardening experts (vegetables, fruits and berries) for technical support for the project beneficiaries 1.2.1.2. to identify and cooperate with at least 5 plant nurseries to provide phenological and phytosanitary analysis of origin. 1.2.1.3. To do market research on new vegetables, fruits and berries varieties and test by at least 2 new varieties for vegetables, fruits and berries that are resistant to drought and disease. 1.2.1.4. To distribute of the new varieties among 150 farmer’s groups 1.2.2. National market analysis for promoting environmental sustainability and food waste reduction 1.2.2.1. To create a roster of national experts in environmental sustainability and food waste reduction 1.2.2.2. To facilitate market research and integrate sustainable mechanisms for effective processing vegetables, fruit and berries in 10 pilot communities 1.2.2.3. To build capacity (workshops and mentorship) of local farmers/families on new processing mechanisms (incl. packaging, storage, and promoting of products) 1.2.2.4. To facilitate promotion of the processed products at the national/local market (exhibitions)
|  | 1.3. At least 40% of farmers in pilot communities of KR applied new agro-technologies | 1.3.1. New technologies integratgion for reducing soil pressure and preventing climate change 1.3.1.1. To establish 60 farmer groups (inclduing 900 vulnerable families) for capacity building on new agro technologies; 1.3.1.2. To build capacity of 20 farmer's groups (15 people per a farmer group; total coverage of at least 300 families) on effective soil conservation techniques for grain crops growing; 1.3.1.3. To research national market capacity and soil analysis for providing and seeding drought-resistant fodder crops 1.3.1.4. To build capacity of 20 farmer groups on the care and preparation of feed sources (forage) and seeding drought-resistant fodder crops 1.3.1.5. To facilitate regular (on quartely or monthly basis) analysis of drought-resistant fodder crops in the regions. 1.3.1.6. To build capacity of local 20 farmer's groups on using new agro technologies for forage crops to increase livestock productivity 1.3.1.7. To facilitate 1-week international study tour for the implementing NGO partners (5-7 people in total) to learn an international experience on climate resistant agriculture and seed management (the host country to be detertmined later)
2. Community Infrastructure for Food Security and improved Nutrition | 2. A more comprehensive approach has been taken by target rural communities to enhance their food and nutrition infrastructure. | 2.1. At least 21 local authorities have identified and prepared documentation for appropriate measures to improve the water supply systems in their community | 2.1.1. Make an announcement to identify beneficiary villages for cooperation in the framework of the project for the preparation of documentation for the rehabilitation of water supply systems. 2.1.2. Draw up a short list of beneficiaries and develop documentation of 21 communities on the drinking water supply system.
|  | 2.2. A total of 12 local authorities have recognized the need for improving their community's irrigation systems and have taken the initiative to prepare documentation outlining the necessary measures. | 2.2.1. Make an announcement to identify beneficiary villages for cooperation in the framework of the project for the preparation of documentation for the rehabilitation of water supply systems. 2.2.2. Draw up a short list of beneficiaries and develop documentation of 12 communities on the irrigation system.
3. National and/or regional policy frameworks in the field of food security and improved nutrition | 3. Favorable conditions for improving food seciruty and enhancing the nutrition of the rural population of Kyrgyzstan established | 3.1. At least 3 policy mechanisms on food security improvement developed and implemented by the national/local authorities | 3.1.1. To build partnership with with national and local authorities, experts and donor community with common interests on national Food Security 3.1.2. To build networking with food and nutrition stakeholders (including SUN CSA) to promote policy mechanisms related to food security 3.1.3. To conduct media campaigns to raise public and key stakeholders' awareness on food security and good nutrition 3.1.4. To onduct policy dialogues with local authorities at district (rayon) and municipal levels on their roles and responsible interventions for food security and good nutrition 3.1.5. To provide expert support (nutrition experts and lawyers) to the working groups established at the local levels for promoting food security and good nutrition in the target regions.